## Assessment Details
BANK ALFAQ DIGITAL — ASSET-BASED RISK ASSESSMENT & TREATMENT REGISTER
Document Classification | Internal
ISO/IEC 27001:2022 References | Bank Alafaq Digital Information Security Risk Assessment and Treatment
Assessment Title | Digital banking services, core banking systems, customer information, employee information, data centres, branches, ATMs, international banking operations and AWS environments used for non-critical development, testing and analytics.
Scope | Bank Alafaq Digital environment implementing ISO/IEC 27001; focus on customer information, digital banking, core systems, employee information, physical banking estate and AWS services, with increasing external cyber threats and cloud-partner security uncertainty.
Context | Bank Alafaq Digital environment; customer trust, applicable Saudi legal/regulatory obligations and cyber threats including ransomware, phishing, DDoS, supply-chain and insider threats.
Method | 5×5 likelihood-impact model. Risk Score = Likelihood × Impact.
Risk Appetite | 14 September 2026
Assessment Date | 14 September 2026
Version | Version 1
Lead Risk Assessor | Information Security Management
Assistant Risk Assessor | Relevant business, IT, compliance, legal and service owners within Bank Alafaq Digital.
Consulted | Top Management – Bank Alafaq Digital
Approved By | Dr. Noura Al-Qahtani – Chief Executive Officer
Next Full Review | 12 September 2027; monthly review while Critical/High current risks remain untreated.
Important Assumption | Residual risk values are projected and must not be treated as accepted until treatment implementation is evidenced and validated.

## Risk Assessment
BANK ALFAQ DIGITAL — ASSET-BASED RISK ASSESSMENT AND TREATMENT REGISTER
Ref | Asset Group | Primary Asset Inventory Ref(s) | Asset / Process | Threat / Risk Event | Vulnerability / Control Gap | Risk Type | Risk Owner | Existing Controls | Likelihood (1-5) | Likelihood Rationale | Impact (1-5) | Impact Rationale | Current Risk Score | Current Risk Level | Treatment Option | Proposed Treatment Action | Annex A / Control Reference | Planning Cost Estimate (SAR) | Treatment Action Owner | Target Date | Progress | Treatment Status | Residual Likelihood (1-5) | Residual Likelihood Rationale | Residual Impact (1-5) | Residual Impact Rationale | Residual Risk Score | Residual Risk Level | Evidence / Source Basis | Comments
R-001 | Information Systems | معلومات العملاء | معلومات العملاء | التصيد والبرمجيات الخبيثة والوصول غير المصرح | تزايد التهديدات السيبرانية وثغرات تطبيقات الخدمات المصرفية الرقمية | Confidentiality, Integrity and Availability | إدارة أمن المعلومات | بوابة البريد الآمن، نظام كشف الاحتيال، إدارة الهوية والوصول، المراقبة الأمنية والاستجابة للحوادث | 4 | استهدفت هجمات التصيد موظفي الإدارة المالية، كما حددت الدراسة تهديدات الفدية وحجب الخدمة وسلسلة التوريد والتهديدات الداخلية | 5 | خسائر مالية وتسريب بيانات وعقوبات تنظيمية وضرر بسمعة البنك |  |  | Modify | تعزيز التوعية، التحقق من التحويلات، المصادقة متعددة العوامل، تحليل معلومات التهديدات ومراجعة الصلاحيات | A.5.10, A.5.15, A.5.16, A.5.17, A.8.5, A.8.15 | 150000 | إدارة أمن المعلومات | أثناء تطبيق نظام إدارة أمن المعلومات | 0% | Open | 2 | الضوابط المقترحة تقلل احتمال الحدوث مع بقاء أثر الحادث مرتفعاً | 5 | قد يبقى الأثر المالي والتنظيمي والسمعة مرتفعاً عند تحقق الاختراق |  |  | خطر مستند إلى هجمات التصيد وبيانات العملاء الواردة في دراسة بنك الآفاق | Treatment evidence should be collected and reviewed before residual-risk acceptance.
R-002 | Core technology | Asset Inventory Ref 2 — Core banking systems / data centres | Core banking, VMware, storage and backups | Ransomware | Broad enterprise exposure and recoverability not fully evidenced | Confidentiality, Integrity, Availability | IT / Infrastructure Management | Trend Micro endpoint; Veritas NetBackup; DR replication | 4 | Ransomware is common and control testing is incomplete. | 5 | Systemic service and transaction disruption could exceed 24 hours. |  |  | Mitigate | Deploy EDR, segmentation, immutable/offline copies and restore exercises | A.8.7; A.8.13; A.8.14; A.8.22; A.5.24 | 1800000 | Infrastructure Manager | 31-Jan-2027 | 0% | Planned | 2 | EDR, isolation and tested immutable copies reduce probability. | 5 | Residual consequence remains severe for core-banking compromise. |  |  | Case study threat environment + backup/DR infrastructure; ransomware identified as a major banking threat. | Quarterly restore and annual failover evidence required.
R-003 | Digital channels | Asset Inventory Ref 3 — Digital banking services | Afaq Plus and Afaq Net | Distributed denial of service | Insufficient upstream scrubbing and single-provider dependency | Availability | Network Management | Palo Alto HA firewalls; FortiWeb WAF; STC internet | 4 | Public banking channels are continuously exposed. | 4 | Customers cannot transact; complaints and regulatory concern likely. |  |  | Mitigate / Transfer | Contract DDoS scrubbing, alternate connectivity, rate limits and runbook | A.8.14; A.8.20; A.8.21 | 900000 | Network Manager | 31-Dec-2026 | 0% | Planned | 2 | Provider scrubbing and tested failover reduce disruption likelihood. | 4 | A successful large attack can still cause major interruption. |  |  | Case study external threat environment: DDoS risk to customer-facing digital banking services. | Include supplier escalation and communications exercise.
R-004 | Network security | Asset Inventory Ref 4 — Network / security infrastructure | Palo Alto firewall estate | Erroneous or unauthorized rule change | No dual review, rollback validation or automated drift monitoring | Integrity, Availability | Network Management | HA pair; Jira Service Management; configuration backups | 4 | A prior deletion caused a three-hour outage. | 5 | Critical banking services and customers may be broadly affected. |  |  | Mitigate | Require dual approval, tested rollback, config backup and drift alerts | A.8.9; A.8.16; A.8.32 | 250000 | Network Manager | 31-Oct-2026 | 0% | Planned | 2 | Independent review and monitoring reduce recurrence. | 4 | A complex change may still cause a major outage. |  |  | Case study incident: firewall rule change caused a 3-hour digital-banking outage. | No emergency change may bypass retrospective review.
R-005 | Business process | Asset Inventory Ref 5 — Payment and business processes | Finance payment process | Phishing / business email compromise | High click/credential rates and slow alert review | Confidentiality, Integrity | Finance / Business Process Owner | Cisco Email Security; fraud detection; some MFA | 4 | Simulation and attempted SAR 150,000 transfer show active exposure. | 5 | Fraud, disclosure and regulatory/reputational consequences. |  |  | Mitigate | Phishing-resistant MFA, call-back verification, one-click reporting and training | A.6.3; A.8.5; A.8.7; A.5.24 | 500000 | Finance Director | 31-Dec-2026 | 0% | Planned | 2 | MFA and independent payment verification lower success. | 4 | A sophisticated compromise could still cause major loss. |  |  | Case study incident: phishing/BEC attempted SAR 150,000 fraudulent transfer. | Marketing and Finance receive monthly targeted exercises.
R-006 | Endpoints | Asset Inventory Ref 6 — Employee devices | Laptops and bank mobile devices | Loss or theft | Incomplete full-disk encryption, MDM and delayed reporting | Confidentiality | IT Support / Endpoint Management | Endpoint antivirus; Active Directory; device inventory | 4 | A marketing laptop was lost unencrypted and reported after 48h. | 5 | Customer campaign data exposure and regulator/customer notification. |  |  | Mitigate | Enforce FDE, MDM, remote wipe and four-hour reporting | A.8.1; A.8.24; A.6.8 | 1100000 | IT Support Manager | 30-Nov-2026 | 0% | Planned | 2 | Encryption and remote controls reduce disclosure probability. | 4 | Loss of an unlocked/compromised device remains major. |  |  | Case study incident: lost marketing laptop contained customer data and was not encrypted. | 100% inventory reconciliation and encryption evidence.
R-007 | People and access | Asset Inventory Ref 7 — Employee information / file services | HR shares and enterprise file services | Unauthorized access by excessive privileges | Inherited access and no complete periodic recertification | Confidentiality | HR / Information Systems Owner | Active Directory groups; manager requests | 4 | Excess access existed for an unknown period. | 4 | Sensitive employee data could be viewed or altered. |  |  | Mitigate | RBAC cleanup and quarterly owner recertification | A.5.15; A.5.16; A.5.18; A.8.3 | 200000 | Identity and Access Manager | 31-Dec-2026 | 0% | Planned | 2 | Owner recertification reduces persistent excess access. | 4 | Mis-provisioning can still have major employee privacy impact. |  |  | Case study incident: IT staff retained inappropriate access to HR files; periodic review gap. | First HR recertification is an audit evidence priority.
R-008 | Identity | Asset Inventory Ref 8 — Privileged identities | Privileged accounts | Credential compromise or misuse | No PAM; passwords are manually administered and may be shared | Confidentiality, Integrity, Availability | Information Security Management | RSA SecurID for some sensitive remote access; AD policies | 4 | High privilege and weak custody make compromise likely. | 5 | An administrator can alter systems, data, logs and security controls. |  |  | Mitigate | PAM vault, named accounts, MFA, session recording and JIT access | A.5.17; A.8.2; A.8.5; A.8.15 | 1600000 | Information Security Management / IT Management | 28-Feb-2027 | 0% | Planned | 2 | PAM/MFA/JIT substantially reduce credential misuse. | 5 | Residual privileged compromise could remain severe. |  |  | Case study: no PAM; privileged passwords administered manually / sharing risk. | CEO visibility until coverage reaches 95%.
R-009 | Digital certificates | Asset Inventory Ref 9 — Digital certificates | Public web and API TLS certificates | Certificate expiry | Manual inventory and renewal monitoring | Availability, Confidentiality | Infrastructure Management | Vendor certificates; manual calendar reminders | 3 | A certificate expired for four hours six months ago. | 4 | Digital service trust and availability are materially affected. |  |  | Mitigate | Central inventory, 60/30/14/7-day alerts and auto-renewal | A.8.9; A.8.16; A.8.21; A.8.24 | 120000 | Infrastructure Manager | 31-Oct-2026 | 0% | Planned | 1 | Automated ownership and alerts make recurrence rare. | 4 | Impact remains major if renewal still fails. |  |  | Case study incident: SSL/TLS certificate expired and services were affected for about 4 hours. | Disable TLS 1.0/1.1 in the same change programme.
R-010 | Vulnerability management | Asset Inventory Ref 10 — Core systems / applications / network devices | Servers, applications and network devices | Exploitation of unpatched vulnerability | Quarterly scanning and incomplete remediation SLA enforcement | Confidentiality, Integrity, Availability | IT / Vulnerability Management | Qualys external scans; Jira; vendor patching | 5 | Known High issues remain open and threat activity is continuous. | 5 | Exploitation may compromise regulated data and critical services. |  |  | Mitigate | Weekly scans; 72h Critical/15-day High SLA; exception board and retest | A.8.8; A.8.29; A.8.32 | 750000 | Vulnerability Manager | 30-Nov-2026 | 0% | Planned | 2 | Faster detection, ownership and validation reduce likelihood. | 5 | A zero-day against a critical service remains severe. |  |  | Case study: 3 High and 7 Medium online-banking findings; some older vulnerabilities remained unresolved. | Report aging and recurrence monthly.
R-011 | Monitoring | Asset Inventory Ref 11 — Security logs and monitoring | Logs and security devices | Inaccurate event sequence | Up to seven-minute clock drift and no standard NTP policy | Integrity | Infrastructure Management | Local/device time sources; central Syslog | 4 | Known drift is widespread enough to affect correlation. | 3 | Investigation, fraud analysis and evidence reliability are impaired. |  |  | Mitigate | Redundant authenticated NTP and daily drift alerting | A.8.17 | 90000 | Infrastructure Manager | 31-Oct-2026 | 0% | Planned | 1 | Authoritative NTP and alerting make harmful drift rare. | 3 | A time service failure still has moderate investigative impact. |  |  | Case-study annex A.8.17: inconsistent time sources and up to 7-minute log difference. | Target drift below one second for critical systems.
R-012 | Cloud services | Asset Inventory Ref 12 — AWS development / test / analytics | AWS dev/test/analytics | Cloud misconfiguration or credential exposure | No comprehensive cloud policy, data rules, CSPM or shared model | Confidentiality, Integrity | Cloud Service Owner | Use limited to non-critical workloads; AWS native controls | 3 | Cloud use is active and governance gaps are documented. | 5 | Credentials or copied bank information could create major breach. |  |  | Mitigate | Cloud policy, account baseline, CSPM, least privilege, encryption and exit plan | A.5.23; A.8.9; A.8.24 | 700000 | Cloud Service Owner | 31-Jan-2027 | 0% | Planned | 2 | Guardrails and CSPM reduce misconfiguration likelihood. | 4 | Remaining scoped cloud data has major potential impact. |  |  | Case-study annex A.5.23: AWS used without complete cloud-risk assessment/policy/shared-responsibility definition. | Prohibit Restricted production data unless separately approved.
R-013 | Suppliers | Asset Inventory Ref 13 — Partner / supplier services | External mobile application developer | Supply-chain compromise | Security due diligence, clauses, SBOM and testing not fully evidenced | Confidentiality, Integrity, Availability | Procurement / Supplier Management | Contract; internal developers; production review | 3 | External code contributes to an internet-facing banking app. | 5 | Malicious/vulnerable code may compromise many customers. |  |  | Mitigate / Transfer | Due diligence, security clauses, SBOM, repository control and testing | A.5.19; A.5.20; A.5.21; A.5.22; A.8.30 | 400000 | Procurement / Development | 31-Jan-2027 | 0% | Planned | 2 | Security gates and contract assurance reduce introduction risk. | 4 | Supplier compromise can still cause major impact. |  |  | Case study: external mobile-application developer is a key supplier; supplier/security governance requires strengthening. | Assess ATM maintenance and STC as critical suppliers too.
R-014 | Development | Asset Inventory Ref 14 — Development and test environments | Development/test/staging environments | Exposure of production data or lateral movement | Isolation is intended but masking and enforcement are not evidenced | Confidentiality | Development Management | Separate VMware environments; GitLab permissions | 3 | Complex environments and developer access make error plausible. | 5 | Real customer data exposure would have severe consequences. |  |  | Mitigate | Mask data, enforce network separation, restrict access and secure disposal | A.8.11; A.8.31; A.8.33 | 350000 | Development Manager | 31-Dec-2026 | 0% | Planned | 1 | Masking and enforced isolation make exposure unlikely. | 5 | Any real-data breach would remain severe. |  |  | Case study guidance: real production data used in testing; gap linked to A.8.11/A.8.31/A.8.33. | Production data requires CISO/Privacy approval and time limit.
R-015 | Information handling | Asset Inventory Ref 15 — Information handling / removable media | Endpoints, printing and removable media | Malicious or accidental exfiltration | No comprehensive DLP/USB/print monitoring baseline | Confidentiality | Information Security Management | Endpoint protection; email/web controls; physical security | 3 | Large workforce and sensitive datasets create credible insider risk. | 5 | Customer, employee or transaction information may be exposed. |  |  | Mitigate | DLP, USB control, print logging, awareness and behavioural monitoring | A.5.10; A.7.10; A.8.12 | 1200000 | CISO / IT Support | 31-Mar-2027 | 0% | Planned | 2 | Layered controls reduce opportunity and improve detection. | 4 | Authorized insiders can still cause major disclosure. |  |  | Case study: sensitive bank/customer information across endpoints and removable/printing channels; DLP maturity gap. | Monitoring must be proportionate and legally reviewed.
R-016 | Resilience | Asset Inventory Ref 16 — Backups / disaster recovery | Backups and Jeddah DR site | Restore/failover failure | Capacity and end-to-end recovery evidence are incomplete | Integrity, Availability | Business Continuity Management | Veritas NetBackup; tape library; DR replication | 3 | Technology exists but successful service recovery is not evidenced. | 5 | Prolonged systemic outage and transaction reconciliation impact. |  |  | Mitigate | Immutable 3-2-1 copies, quarterly restores and annual full failover | A.5.29; A.5.30; A.8.13; A.8.14 | 1400000 | BCM Manager | 31-Mar-2027 | 0% | Planned | 1 | Frequent tested recovery reduces failure likelihood. | 5 | A regional or cyber crisis can still have severe impact. |  |  | Case study: Jeddah DR site, backup infrastructure and continuity dependencies require tested recoverability. | Core RTO 2h/RPO 15m; payments RTO 1h/RPO ≤5m.
R-017 | Physical | Asset Inventory Ref 17 — Branches / ATMs / equipment rooms | Branches, ATMs and equipment rooms | Intrusion or tampering | Distributed estate and inconsistent review of access/tamper evidence | Confidentiality, Integrity, Availability | Facilities Management | Cards/biometrics at HQ/DC; CCTV; guards; ATM maintenance | 3 | Many public and distributed locations increase exposure. | 4 | Tampering may enable fraud or service compromise. |  |  | Mitigate / Transfer | Access recertification, tamper sensors, CCTV retention and inspections | A.7.1; A.7.2; A.7.4; A.7.8; A.7.9 | 850000 | Facilities Manager | 31-Jan-2027 | 0% | Planned | 2 | Monitoring and inspection reduce successful intrusion. | 4 | A successful physical compromise remains major. |  |  | Case study: 25 branches, 150 ATMs and physical security infrastructure are in ISMS scope. | Supplier maintenance access must be logged and escorted.
R-018 | Security operations | Asset Inventory Ref 18 — SOC / central security logs | Central logs and SOC | Delayed detection and containment | No SIEM; manual analysis and incomplete source coverage | Confidentiality, Integrity, Availability | Security Operations / SOC | Central Syslog; SOC with eight analysts; device logs | 4 | Prior outage/BEC detection took 45 minutes to two hours. | 5 | Delayed containment can expand breach, fraud and outage. |  |  | Mitigate | Deploy SIEM, priority use cases, 24x7 on-call and response SLAs | A.5.25; A.8.15; A.8.16; A.8.17 | 2200000 | SOC Manager | 31-Jan-2027 | 0% | Planned | 2 | Central correlation and paging reduce detection delay. | 4 | Novel attacks may still evade detection and cause major impact. |  |  | Case study: central Syslog exists but no SIEM; analysis is manual; earlier incidents show detection delay. | Coverage target ≥95%; critical MTTD <15 minutes.
R-019 | Privacy | Asset Inventory Ref 19 — Customer and employee PII | Customer and employee PII | Regulatory/privacy process failure | Manual DSAR, unclear retention, no automated discovery/deletion or DPIA | Confidentiality, Compliance | Legal / Privacy / Compliance | Onboarding consent; Legal/Compliance review; access controls | 4 | Known process gaps affect large volumes of PII. | 5 | PDPL/SDAIA breach, customer harm, penalties and reputation. |  |  | Mitigate | PII inventory, retention schedule, DSAR workflow, DPIA and secure deletion | A.5.31; A.5.33; A.5.34; A.8.10 | 900000 | Legal / Privacy Manager | 28-Feb-2027 | 0% | Planned | 2 | Governed lifecycle and automation reduce noncompliance. | 4 | Large-scale PII processing retains major inherent consequence. |  |  | Case-study annex/privacy context: large volumes of customer/employee PII; retention/deletion/privacy processes require formalization. | Legal must confirm exact statutory deadlines and retention.
R-020 | Software lifecycle | Asset Inventory Ref 20 — Bank software / intellectual property | Bank software and open-source components | Unlicensed or vulnerable software | No comprehensive licence audit, SCA or bank IP standard | Confidentiality, Integrity, Legal | Development / IT Management | GitLab Enterprise; development team; vendor contracts | 3 | Open-source and legacy software are used without complete evidence. | 4 | Security exploit, legal claim or unsupported software may disrupt service. |  |  | Mitigate | Allow-list, SCA, licence audit, IP rules and secure coding standard | A.5.32; A.8.19; A.8.25; A.8.28 | 450000 | Development Manager | 31-Jan-2027 | 0% | Planned | 2 | Inventory and automated SCA reduce undetected exposure. | 3 | Residual legal/technical effect is moderate with controls. |  |  | Case-study annex A.5.32: software/IP-rights and licence-management policy is unclear. | Track SBOMs and licence obligations per release.

## Summary
BANK ALFAQ DIGITAL — RISK PORTFOLIO SUMMARY
Risk Level | Current Count | Projected Residual Count | Management Position |  | KPI | Value
Critical |  |  | Immediate treatment and executive visibility. |  | Total Risks
High |  |  | Treatment required and formal governance oversight. |  | Current Critical + High
Medium |  |  | Treatment plan / approval and quarterly monitoring. |  | Projected Residual Critical + High
Low |  |  | May be accepted with documented rationale and monitoring. |  | Treatments Planned
| 14 September 2026 |  |  |  | Total Planning Cost (SAR)
[5 empty] | Assessment Date | 14 September 2026
5×5 RISK MATRIX — SCORE / LEVEL
5 | 5 Medium | 10 Medium | 15 High | 20 Critical | 25 Critical
4 | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical
3 | 3 Low | 6 Medium | 9 Medium | 12 High | 15 High
2 | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 Medium
1 | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium
Impact ↓ / Likelihood → | 1 | 2 | 3 | 4 | 5

## Methodology
BANK ALFAQ DIGITAL — APPROVED RISK SCORING & TREATMENT RULES
Likelihood Score | Descriptor | Guidance | Impact Score | Descriptor
1 | Remote / Rare | Improbable under normal conditions; exceptional circumstances. | 1 | Insignificant
2 | Unlikely | Low chance; may occur in exceptional circumstances. | 2 | Minor
3 | Possible | Realistic possibility in the current environment. | 3 | Moderate
4 | Probable / Likely | More likely to occur; material exposure or prior occurrence. | 4 | Major
5 | Highly Probable / Almost Certain | Strong evidence, active threat or frequent occurrence. | 5 | Catastrophic
Risk Level | Score Range | Treatment / Acceptance Requirement
Low | 1–4 | May be accepted with documented rationale and monitoring.
Medium | 5–10 | Requires a documented treatment plan, named owner, target date and management approval where accepted.
High | 11–15 | Requires formal treatment and governance oversight; residual acceptance requires senior management approval and justification.
Critical | 16–25 | Outside normal appetite; immediate escalation and treatment required; executive approval for any temporary acceptance.
Risk Acceptance Criteria (Bank Alafaq Digital) | A risk may be recommended for acceptance when the score is 4 or less, when known changes mean the risk will exist for three months or less, or when agreed direct/indirect benefits outweigh the impact. Reasons must be documented.
Treatment Option | Meaning
Accept | Retain the risk with documented approval where permitted by appetite.
Avoid | Stop/change the activity causing the risk.
Mitigate | Reduce likelihood and/or impact using controls.
Transfer | Shift/share financial or operational exposure through contract, insurance or supplier arrangements.
Key Rule | Value
Current Risk Score | Likelihood × Impact
Residual Risk | Projected until treatment implementation is evidenced and validated.
Review Trigger | At least annually and upon significant change, incident, control failure or missed treatment due date.

## Sources
BANK ALFAQ DIGITAL — SOURCE & TRACEABILITY REGISTER
Bank Alafaq Digital Case Study / Risk Assessment Package | Context, assets, threats, vulnerabilities, existing controls and assessment basis | Primary source | Supplied Bank Alafaq Digital package.
Bank Alafaq Digital Information Asset Inventory | Asset names, owners, classification and scope cross-linking | Supporting register | Customer information is the populated asset in the supplied inventory; remaining asset references are mapped to the stated assessment scope.
REQUIRED-ISMS-FORM-06-1 Asset-Based Risk Tool | 5×5 risk assessment structure, treatment fields and control references | Primary template | Supplied CertiKit-based asset risk workbook.
REQUIRED1-ISMS-FORM-06-2 Statement of Applicability | Annex A control applicability and implementation context | Supporting ISMS record | Supplied Bank Alafaq Digital SoA workbook.
ISO/IEC 27001:2022 | Clauses 6.1.2, 6.1.3 and 8.2/8.3 | Standard reference | Risk assessment and treatment framework.
Information Asset Inventory – Final | Asset reference cross-linking | Supporting register | Primary asset references are shown in the Risk Assessment sheet.